State of Alaska

Department of Environmental Conservation

SPAR Division

Public Web Access to PERP Database

Functional Specification Draft

## Content

Purpose…………………………………………………………………	3

Relevant Documents…………………………………………………...	3

Prototypes……………………………………………………………… 	3

Environment……………………………………………………………	3

Process Management………………………………………………..…	3

Data Representation……………………………………………………	4

Tasks…………………………………………………………………...	4

Estimate………………………………………………………………..	7

Appendix………………………………………………………………	8

1. Purpose

The purpose of “Public Web Access to PERP Database Software Functional Specification” is to identify all requirements for successful completion of the above mentioned project.

2. Relevant Documents

These documents will be used as general guidelines for the report generation:

Alaska Department of Environmental Conservation – Quarterly Report of Oil and Hazardous Substance Response

Alaska Department of Environmental Conservation – Statewide Summary of Oil and Hazardous Substance Spill Data

Alaska Department of Environmental Conservation – Significant Responses page on PERP Internet site at http://www.state.ak.us/dec/dspar/perp/respnew.htm.

3. Prototypes

There are three separate web pages currently available for viewing at

http://jnu-web3/spar/perp/internet/prototypes2/spillshome.htm

a) The suggested template page mentioned in task 1a).

b) The main menu for the generation of tables and graphs.

c) The main menu for the Significant Responses.

Please see the Appendix for detailed information on prototypes.

4. Environment

- Access to the main page will be provided through the Department of Environmental Conservation public web server. This site will be designed to support both Netscape Navigator 6.0 and MS Internet Explorer 5.0 or better. We have to be able to use the Document Object Model for our SVG pages.  An additional free viewer from Adobe will be needed to support SVG graphs (http://www.adobe.com/svg/viewer/install/main.html).

- Application will be stored in the form of Active Server Pages (ASP) on Microsoft Internet Information Server to provide live access to the PERP database.

- The current environment for all databases within the SPAR Division is Microsoft's SQL Server version 7.0.

5. Process Management

5.1 Change Control

All changes requested after this document has been revised and approved will be evaluated and analyzed to determine their impact on schedule, cost, and potential risk to the project’s functionality.

If the proclaimed change is considered a necessary enhancement/feature for this version of the project, the project’s time schedule will have to be adjusted accordingly.

5.2 Variables

Every other change to the schedule that is not implied by the paragraph above will be discussed in detail with the customer.  There are two categories:

- Unexpected problems might occur during the application development.  This includes browser compatibility issues and some minor changes to the ASP structure described in Tasks below.

- Feedback from the customer.  The schedule will be met only if the customer provides timely and detailed response. (It is still not clear whether or not brine should be included on the graphs.  Some design issues such as the color scheme and the background are still uncertain.)

6. Data Representation

Data will be presented in three major forms:

- Dynamic Graphs - in form of pie charts (spills by size class, spills by product, spills by source, spills by cause), line and bar graphs.  Particular graph will be chosen automatically, based on the input from the user.

- Tables - spill trends for all spills, or broken down to individual categories and subcategories.  Tables are associated with particular graphs.

- Significant Responses – in the format presented on PERP home page (see Relevant Documents)

7. Tasks

7.1 General

This new application will be separate from any existing applications and the existing PERP website.

We will not be able to meet the Bobby Standard (standard of HTML pages for disabled persons) for the newly created pages for the following reason.  They will violate the W3C priority 1 requirement – “ Ensure that the pages are usable when scripts, applets, or other programmatic objects are turned off or not supported.”  It is not possible to create a user-friendly interface for our application without using client-side scripts.

“Breadcrumbs” will not be used to display location in the title bar.  There are two reasons – the new website will only be one level deep with a link back to PERP home; therefore, no navigational aid is really needed.  The second reason is that it will be located on a different server with a different directory structure.

7,2 Task1 – Tables and Graphs

.

- Write the SVG code that will draw a graph or a pie chart based upon the data input from the html page (formed by ASP).  There will be two different SVG files, one for pie charts and one for all other graphs. The graphs will be interactive and provide additional information whenever the user moves the mouse over the particular object (pie slice, bar, point on the graph).  In addition, the graphs will use two Y coordinate scales that will be adjusted automatically based on the data input. Correct labels will also be generated. The segment marks on the y axes will not be labeled, since the user can see the exact value using the DisplayInfo() function triggered by the mouseover event on the object (point/bar). These marks would also take up too much horizontal space. The labels for the x-axis will be in a 45-degree angle to the x-axis.

- Create a user-friendly form to gather information. The screenshot of this menu is included in the appendix. Please note that this form will be designed to incorporate additional expansions in future versions of this application. The goal for this phase is to be able to generate all graphs and tables from DEC Quarterly Report of Oil and Hazardous Substance and Statewide Summary of Oil and Hazardous Substance Spill Data.  Additional graphs might be included upon request, but are not part of the current schedule estimate. This form will be generated by an ASP page and populated with data from the PERP database, the date range will be derived from current server date (see the Sig. Responses prototype).  The user will be able to enter a date (within a single year interval) or all years for reports on all data, and select the scope of the report (regulated/non- regulated, include/exclude Brine). When the “all years” option is chosen, the months will be set to blank.  There will be four additional options to choose from, first one required and the additional three optional.  The first three are main category and two sub categories (for example Spills by ProductRefined OilAsphalt), next option specifies one additional level of detail (for example Asphalt broken down by Area, etc.). The last option is the selection of units, in which the data was reported and will be displayed. The units are currently Count, Gallons, and Pounds.  However; when the All Years option is chosen and a pie chart will be displayed, the options are limited to pounds or Gallons only.

Please refer to the flow chart on page six for additional information on what type of graph will be generated.

- Process this form via another ASP.  Based on the user input, the application will decide what kind of graph and/or table will be displayed.  This page will then turn control over to one of four ASP pages.

- Set up individual ASP pages.  These will call the stored SQL procedure to retrieve the needed data and to create the html to set up the particular graph and table properly.  The plan is to display the table on top of the page and the associated graph below.  Other alternatives are open for discussion.

- Write the code for the stored procedure. This stored procedure will take these parameters – Begin Month, End Month, Year, Scope, Class, Item , Item Detail, Graph Detail, Units.

7.3 Task2 – Significant Responses

- Create a main menu. The screenshot of this menu is included in the appendix. A simple form to allow a user to choose a time interval within a single year.  Similar to the date input in task 1 b).

- Modify the Spill Table. The present Comments field will hold the significant response text, but the existing LocationDesc field will be changed to a bit field Significant.

- ASP pages to process the form. The first ASP page will construct a query based upon the user input and retrieve the date, spillID and the spill’s name. It will then present the page in a format similar to the one on PERP Significant Responses web page (see Relevant Documents). Clicking on the name will call a second asp page that will display the name and the text. Please refer to the prototype for visual information.

- ASP page to display the information. This additional page might be necessary to display the actual significant response data, after the user clicks on the corresponding header.

- Write the code for the stored procedure.  This stored procedure will take only the date range as the parameters (Begin Month, End Month, Year) and return the information mentioned above.

8. Estimate

| ## Task 1 – Tables and Graphs | ## Estimated work hours |
| --- | --- |
| a) Write the SVG code (pie charts + other graphs) | (15-20)+(15-20) |
| b) Create the ASP for main input form | 18-20 |
| c) Form processing ASP | 8-10 |
| d) Set up the four ASPs for table and graph creation | 35-45 |
| e) Write the code for the stored procedure | 15-18 |

| ## Task 2 – Significant Responses | ## Estimated Work Hours |
| --- | --- |
| a) Create a main menu | 4-6 |
| b) Modify the spill table | 1 |
| c) Create the ASP to process the form | 15-20 |
| d) ASP to display the response information | 5-8 |
| e) Write the code for the stored procedure | 1 |

## Technical Documentation: 15 Work Hours

#### Total Work Hours = 147 – 185

## 9. Appendix

The first prototype is only a template page, created using CSS.  It was designed to meet the Bobby Standard, however, it was not yet tested.

The second prototype is the main interface for graph and table generation – see the attached screenshot.  The first gray field will provide the user with information about how to use this form.  Then the date range will be selected.  The All Years option is available in the year menu to select the complete date range. In this case, the months set blank. The Scope menu is pretty self-explanatory.

Then the user selects the option on which to categorize.  The Item menu will be than populated from the database.  Upon selecting a Specific Item, the Item Detail menu will be set up, again from the database. The Graph Detail menu is available only if Specific Item or All Spills option is selected.  The last menu lets the user select the units in which the spills were reported. The default is Count.

“Department“ is misspelled

The Statewide Spills DB has been in production since July 1, 1995.

The third prototype is this simple menu. Select the date range and click the click for overview of the responses. Clicking on the header on the next page will take you to the response text.

Following are the screen shots of the graphs.  Please note that they are currently under development

This one is purely experimental and offers the same information as the last graph above. Moving the mouse over the circle would display the count value.